## General
STATEMENT OF WORK
Create a tool for network sizing and traffic study related to the creation of new networks for Smart Grid solutions. In particular, enable logical transition from the SRS for robust analysis of functional and volumetric requirements for particular network transactions. A fully functional prototype tool will be available at the conclusion of this task force.
PRODUCT OBJECTIVES
I.D. | Objective
1 | Create a mechanism to Parse data flow records, breakdown data flow records to isolate App (level 7) vs network traffic and identify primary and alternative paths.
2 | Provide a user friendly / productive environment which allows each to configure to their own communication requirements
3 | Provide a vehicle for logical expansion by other developers. The prototype and supporting materials should enable the progression to a production-level product.
CONSTRAINTS / ASSUMPTIONS
I.D. | Field | Metric 1 | Metric 2 | Field 3
1 | Time | Deadline, Dec 31, 2010
2 | Costs | Materials 0$ | Resources 0$
3 | Scope | Represent the latest SRS and Requirements | Prototype product
4 | Other | Current version on Access 2000 | It is quite important to maintain syncronized: 1) Reference Diagram 2) Requirements.xls 3) SRS
STAKEHOLDERS
I.D. | Name | Role | Company | Telephone | Email | Skype | Time zone
1 | Jerry Armes | Owner / Architect / Developer | Micronet Communications, Inc. | 972-422-7200 | jarmes@micronetcom.com |  | CST
2 | Ron Cunningham | Consultant / Primary Advisor | American Electric Power | 918-599-2622 | rtcunningham@aep.com |  | CST
3 | Matt Gillmore | Consultant / Task Force Lead | Consumers Energy | 517-788-0658 | mkgillmore@cmsenergy.com |  | EST
3 | Juan Oliver | Product Coordinator | IAP Solutions | (+34) 911801111 | juan.oliver@iapsolutions.com |  | CET
4 | David Gosch |  | IAP Solutions | 650-245-4057 | david.gosch@iapsolutions.com |  | PST
5 | Klaus Bender |  | UTC | 202-833-6803 | klaus.bender@utc.org |  | MST
6 | Kelly Flowers |  | DTE Energy | 313-235-1651 | flowersk@dteenergy.com |  | EST
7 | Jorjeta Jetcheva |  | Itron | 509-891-3271 | jorjeta.jetcheva@itron.com |  | PST

## Actors
I.D. | Actor | Description | Main functionalities
I.D. | Who is going to interact with our product (person or system) | A rationale or description of the actor | Which are the main functionalities that this actor is going to execute
1 | Requirements Spreadsheet | Data interface for the project | Upload into database
2 | Database Administration | Database maintenance, application development | Include user profiles and export capabilities (CSV format)
3 | Utility network engineering | Person or group in charge of network planning | Forecast network bandwith
4 | Vendor architect / consultant | network planning | recommend and verify network technologies / parameters
5 | Regulatory / policy maker | DOE, NIST, etc…

## Product Backlog
ROADMAP
[6 empty] | Rel 1 | Rel 2 | Rel 3 | Future
I.D. | Name | Surname | Priority | Difficulty | Notes, rational | 6-Sep | 02-nov | 30-Dec | 2011 | Status comment
Unique I.D. | Name of the action. An action can be: * Any single task identified and required in one release, ie: to create a CVS repository * A main functionality that needs to be implemented. These are fat grain functionalities that will be described in deep in the Use Case Tab | Any specialization of the Name field, ie the name field can be Network Inventory and the Surname would be Import | Select 1 - 3, with 1 highest | Relative level of dificulty related to the others action. Select 1 - 5, with 5 highest.
1 | data flow ref pseudo code parsing routines for alternative comm-paths and multi-actor from or to actors |  |  |  |  | X |  |  |  | done, first pass
2 | view and select which comm-path is to be used for each selected payload requirement set (child) | will require some data input & db table work |  |  | Network level connection only |  |  | X |  | open
3 | flexible set of queries for that includes: which comm-path (one per parent), which use cases (all or a subset), which payloads (by type, all or a subset), what networks (all or a subset or a specific one), what actors (all or a subset) |  |  |  | Still need to add network crossings (done by15th of November) |  |  | X |  | open
4 | identify the requirements and payloads that traverse or reside within a specific domain's network | will require some data input & db table work | Last priority for third release 15th Nov |  | some actors Do not have domains, eg. DAP |  |  | X
5 | export (csv), and reporting capabilities of query results | first pass |  |  |  |  | X |  |  | done
6 | user and project profiles |  |  |  | infrastructure forms to profile projects |  | X |  |  | done
7 | parsing the base requirements for specific deployment typology: deployment scope/scale (quantity and types), specifying requirement variable or ranged values, and/or allowing user to modify other base requirement quantified metrics | basic infrastructure form |  |  |  |  | X |  |  | open, Sept 24 demo
8 | aggregation of the query and parsed deployment requirements e.g. daily, hourly, per interface, per network |  |  |  | IT need some more discussion (15th November) |  |  | X
9 | flexible set of queries for that includes: which comm-path (one per parent), which use cases (all or a subset), which payloads (by type, all or a subset), what networks (all or a subset or a specific one), what actors (all or a subset) release 3 | SAME THAT ISSUE 3 |  |  | Parent network linkage, complicates this request. |  |  | X
10 | migrate to a different dbms and UI environment e.g. SourceForge with advanced features and capabilities | [7 empty] | X
11 | tools to format extracted data for into into 3rd party network analysis tools | in the future more than CVS export (Ron) | [6 empty] | X
12 | post database to SG-Network website, with use instructions | in each release |  |  |  | X |  |  |  | done
13 | survey community for additional features and capabilities | in each release |  |  |  |  | X |  |  | Ron, open
14 | vetting of release features | in each release |  |  |  |  | X |  |  | Ron, final users, open
15 | add full text of Actor names | Table modifications |  |  |  | X |  |  |  | done
16 | add full text of Payload cryptic names | Table modifications |  |  |  | X |  |  |  | done
17 | add in security CIA 3x3 matrix for interface control measures |  |  |  | still not decided how we are going to do that (15th November) |  |  | X |  | open, requires specification
18 | add in high water mark for aggregation of payload security C-I-As at interface level |  |  |  | still not decided how we are going to do that (15th November) |  |  | X |  | open, requires specification
19 | Direct input/maintenance of Content within database via e.g. form based(?) UI That means that the new values are not introduced using the spreadsheet | In terms of maint recomends 1) Tie a form from the excel table 2) There is table called execappconectionsimport 3)Got to the APlications2Aplications tabel and erased 4) Do the same for the networkconectionstable 5)Run all of the parcel software routines to map the content in the proper tables 6) There are other table that need to be maintained by hand e.g CloudCrossings every time the system diagrams changes | Last priority for third release 15th Nov |  |  |  |  | X
20 | to ensure the accuracy and validity of the data in the tables (e.g. Use Cases, Actors, Payloads, etc.) |  |  |  | requires independent validation. SRS and Req XLS must be represented accurately. Automated method preferred. |  |  | X |  | open, requires process / owner SOFTWARE UPDATING ON PAYLOADS AND ACTORS FROM THE EXCEL SPREADSHEET HAS BEEN IMPLEMETTED (15TH Nov)
21 | As new versions of the System Requirements spreadsheet are issued, there will be records that do not fit a template in the Record Parsing routine | XLS ver 4.1 release | [5 empty] | X |  | Open
22 | Addition of a User Profile capability | [5 empty] | X |  |  | done
23 | Port to Access 2007 | [6 empty] | X
24 | add full text of Payload cryptic names | English version of Payload Names | [5 empty] | X |  | It needs independent verification 15th NOV
25 | Add full text of Actor names | English version of Actor Names | [5 empty] | X |  | It needs independent verification 15th NOV
26 | Data flow psedo code | Enhancements for higher bracket levels | [5 empty] | X |  | It needs independent verification 15th NOV
27 | export and reporting capabilities of query results | enhancements | [5 empty] | X |  | Done 15th Nov in CVS format
28 | Traffic Analysis | Utilize the How Often statistics |  |  | must find a way to normalize these fields |  |  |  | x
29 | Add a table to the DDB for Documentation of the version | [6 empty] | x |  | Done 15th Nov
Note on A11: Author: Removed, this functionality goes into User Profiles
Note on I8: Author: Delayed due to its low priority
Note on A18: Author: Waiting for end users assesment
Note on A21: Author: Delayed due to lack of input form rest of the group
Note on A22: Author: Delayed due to lack of input form rest of the group
Note on A25: Author: It has been decided to implement this change with the last versions of SRS. Dec Release
Note on A30: Author: It has been decided to implement this change with the last versions of SRS. Dec Release
Note on A28: Author: Delayed due to lack of input form rest of the group
Note on A29: Author: Delayed due to lack of input form rest of the group
Note on H3: Author: Release delivery has been delayed, to allow implement those decisions taken during Fort Lauderdale meeting
Note on I6: Author: Moved to the next release
Note on A13: Author: Same that issue 3 can be removed

## Use cases
Use Case I.D. | Name | Use Context | Scope | Level | Main Actor | Stakeholders and Interest | Precondition | Minimal guaranties | Guaranties if success | Trigger | Main success scenario | Extensions | Data / Technology variations | Related Information
Unique ID of the use case. Base number is from Product Backlog | The name is the use case goal as a short active verb phrase | a longer statement of the context of use if needed, its normal occurrence conditions | Design scope, what system is being considered "black-box under design", can be a "Company" use case or a "Departament" use case or a "System" use case | Can be a summary use case or a user-goal or a sub function | A role name for the primary actor | List of stakeholders and key interest in the use case | what we expect is the state of the world | how the interest are protected under all exits(ie. Databse integrity maintained) | Success Criteria | what starts the use case | put here the steps of the scenario from trigger to goal delivery and any cleanup after <step #><action description> | put here the extensions, one at a time, each referring to the step of the main scenario <step altered><condition>: <action or sub use case> | put here the variations that will cause eventual bifurcation in the scenario | whatever necessary for additional information
28.1 |  | Templates will be established in software capable of analyzing each 'How Often' column to break out constituent variables for the purpose of supporting traffic analysis.
28.2 |  | Data to be read from the 'How Often' column, and combined with additional stored data from the User Profile as necessary, to calculate a level of traffic for each Payload Delivery row specified in the System Requirements Spreadsheet
28.3 |  | Calculated traffic levels will be spread over the hours specified in the 'Daily Occurrence" column of the System Requirements Spreadsheet
28.4 |  | Where insufficient information is present in the 'How Often' and/or 'Daily Occurrence' columns, to make a reasonable estimate of the hourly traffic, algorithms are to be developed, utilizing the information that is available, with extrapolations using models such as Poisson traffic modeling.
28.5 |  | Provision shall be made to store hourly traffic modeling from each payload delivery row in the System Requirements Spreadsheet, such that queries identifying specific Payloads, Use Cases, Actors, Payload Types, and Cloud Crossings can be summarized and presented in a graphical chart format.

## Sprint Backlog
Use Case I.D. | Name | Priority | Estimated effort | Status | Assigned to
Unique ID of the use case. Base number is from Product Backlog | The name is the use case goal as a short active verb phrase | Inherits priority filed form the Product backlog | Number of person-days required to do the work | One of these: "Not started" "Started" "Finished"
1 | UC1 | 3 | 5 | Started | Juan
2 | UC2 | 2 | 15 | Started | Jerry
3 | UC3 | 3 | 7 | Not Started | N/A
4 | UC4 | 1 | 12 | Not Started | N/A
5 | UC5 | 1 | 6 | Not Started | N/A
6 | UC6 | 1 | 10 | Not Started | N/A
7 | UC7 | 3 | 12 | Not Started | N/A
8 | UC8 | 2 | 7 | Not Started | N/A
9 | UC9 | 2 | 8 | Finished | Ron
10 | UC10 | 1 | 5 | Finished | David
11 | UC11 | 2 | 9 | Finished | Matt

## Burnout statistics
| Use Case I.D. | Unique ID of the use case. Base number is from Product Backlog | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | TOTAL
| Name | The name is the use case goal as a short active verb phrase | UC1 | UC2 | UC3 | UC4 | UC5 | UC6 | UC7 | UC8 | UC9 | UC10 | UC11
| Priority | Inherits priority filed form the Product backlog | 3 | 2 | 3 | 1 | 1 | 1 | 3 | 2 | 2 | 1 | 2
| Estimated effort | Number of person-days required to do the work | 5 | 15 | 7 | 12 | 6 | 10 | 12 | 7 | 8 | 5 | 8 | 95
Development Trace
Day 1 | 90 | Time Spent | bar: UC1 to UC2; UC9 to UC11
|  | Time to deliver | 4 | 14 | 7 | 12 | 6 | 10 | 12 | 7 | 7 | 4 | 7
Day 2 | 88 | Time Spent | UC1: 2; UC2: 2; UC9: 2; UC10: 2; UC11: 2
|  | Time to deliver | 3 | 14 | 7 | 12 | 6 | 10 | 12 | 7 | 6 | 5 | 6
Day 3 | 85 | Time Spent | UC1: 3; UC2: 3; UC9: 3; UC10: 3; UC11: 3
|  | Time to deliver | 4 | 14 | 7 | 12 | 6 | 10 | 12 | 7 | 5 | 3 | 5
Day 4 | 81 | Time Spent | UC1: 4; UC2: 4; UC9: 4; UC10: 4; UC11: 4
|  | Time to deliver | 3 | 13 | 7 | 12 | 6 | 10 | 12 | 7 | 4 | 3 | 4
Day 5 | 75 | Time Spent | UC1: 5; UC2: 5; UC9: 5; UC10: 5; UC11: 5
|  | Time to deliver | 2 | 12 | 7 | 12 | 6 | 10 | 12 | 7 | 3 | 1 | 3
Day 6 | 71 | Time Spent | UC1: 6; UC2: 6; UC9: 6; UC10: 6; UC11: 6
|  | Time to deliver | 2 | 11 | 7 | 12 | 6 | 10 | 12 | 7 | 2 | 0 | 2
Day 7 | 66 | Time Spent | UC1: 7; UC2: 7; UC3: 1; UC9: 7; UC11: 7
|  | Time to deliver | 1 | 10 | 6 | 12 | 6 | 10 | 12 | 7 | 1 |  | 1
Day 8 | 62 | Time Spent | UC1: 8; UC2: 8; UC3: 2; UC9: 8; UC11: 8
|  | Time to deliver | 1 | 9 | 5 | 12 | 6 | 10 | 12 | 7 | 0 |  | 0
Day 9 | 54 | Time Spent | 9 | 9 | 3 | 1 | 1 | 1 | 1 | 1
|  | Time to deliver | 0 | 8 | 4 | 11 | 5 | 9 | 11 | 6
Day 10 | 47 | Time Spent |  | 10 | 4 | 2 | 2 | 2 | 2 | 2
|  | Time to deliver |  | 7 | 3 | 10 | 4 | 8 | 10 | 5
Day 11 | 39 | Time Spent |  | 11 | 5 | 3 | 3 | 3 | 3 | 3
|  | Time to deliver |  | 5 | 2 | 9 | 3 | 7 | 9 | 4
Day 12 | 33 | Time Spent |  | 12 | 6 | 4 | 4 | 4 | 4 | 4
|  | Time to deliver |  | 4 | 1 | 8 | 3 | 6 | 8 | 3
Day 13 | 25 | Time Spent |  | 13 | 7 | 5 | 5 | 5 | 5 | 5
|  | Time to deliver |  | 3 | 0 | 7 | 1 | 5 | 7 | 2
Day 14 | 18 | Time Spent | UC2: 14; UC4: 6; UC5: 6; UC6: 7; UC7: 6; UC8: 6
|  | Time to deliver | UC2: 2; UC4: 6; UC5: 0; UC6: 3; UC7: 6; UC8: 1
Day 15 | 14 | Time Spent | UC2: 15; UC4: 7; UC6: 9; UC7: 7; UC8: 7
|  | Time to deliver | UC2: 0; UC4: 5; UC6: 4; UC7: 5; UC8: 0
| Actual | Estimate
95
Day 1 | 90 | 90
Day 2 | 88 | 85
Day 3 | 85 | 80
Day 4 | 81 | 75
Day 5 | 75 | 70
Day 6 | 71 | 65
Day 7 | 66 | 60
Day 8 | 62 | 55
Day 9 | 54 | 50
Day 10 | 47 | 45
Day 11 | 39 | 40
Day 12 | 33 | 35
Day 13 | 25 | 30
Day 14 | 18 | 25
Day 15 | 14 | 20
Day 16 |  | 15
Day 17 |  | 10
Day 18 |  | 5
Day 19 |  | 0

## Issues
I.D. | Issue | Notes, rationale | Creation Date | Owner (Stakeholders) | Action | Status
1 | options to address the multi-actor actor to actor pairing on 67 payload parents e.g. change to 1 actor from and 1 actor to limit on the parent, or modify data flow ref pseudo code parsing routines |  | 2010-08-25 |  | Jerry would rework the data flow ref pseudo code parsing routines to account for 8 levels of structure and the multi-actor parents Ron will start making the edits to the release 4.1 draft that includes the multi-actor parent data flow ref pseudo code changes | target 10/30/2010 release
2 | need to manage the development process |  | 2010-08-25 | PL | use a rapid development process versus a waterfall approach David & Juan would use the initial roadmap to start populating the software development management template | target 9/30/2010
I.D. | CLOSED ITEMS | Notes, rationale | Creation Date | Owner (Stakeholders) | Action | Status
| need to identify additional resources to perform the additional work items |  | 2010-08-25 | JO, ( PL, JAG) |  | X
| need a feature/capability roadmap (in a need/priority order) to help make the call for those resources and the value back to the industry |  | 2010-08-25 | JO, PL, JAG | Ron would prepare an initial draft of a feature/capability roadmap based on currently documented feature/capability needs, and not get too far into any network traffic modeling tools, focus on what can get accomplished in the next 3-4 months | X
| continue using ACCESS and MS tools for UI development and/or migrate over to a MySQL and OSS SourceForge platform and development approach |  | 2010-08-25 | JAG | continue to use MS ACCESS and associated MS dev tools for any UI needs through the entire prototyping stage, estimated to complete on 12/31/2010 | X
| realize that the SG-Network TF has an anticipated end-of-year completion date |  | 2010-08-25 | PL |  | X
| concerns on dealing with the intellectual property in the added features /capabilities |  | 2010-08-25 |  | The product will be released to sourceforge and become common property. Future consulting and training services surrounding the product can remain the property of that provider. | X

## Hoja1
Use Case I.D. | Unique ID of the use case. Base number is from Product Backlog
Name | The name is the use case goal as a short active verb phrase
Use Context | a longer statement of the context of use if needed, its normal occurrence conditions
Scope | Design scope, what system is being considered "black-box under design", can be a "Company" use case or a "Departament" use case or a "System" use case
Level | Can be a summary use case or a user-goal or a sub function
Main Actor | A role name for the primary actor
Stakeholders and Interest | List of stakeholders and key interest in the use case
Precondition | what we expect is the state of the world
Minimal guaranties | how the interest are protected under all exits(ie. Databse integrity maintained)
Guaranties if success | Success Criteria
Trigger | what starts the use case
Main success scenario | put here the steps of the scenario from trigger to goal delivery and any cleanup after
<step #><action description>
Extensions | put here the extensions, one at a time, each referring to the step of the main scenario
<step altered><condition>: <action or sub use case>
Data / Technology variations | put here the variations that will cause eventual bifurcation in the scenario
Related Information | whatever necessary for additional information
Use Case I.D. | Name | Use Context | Scope | Level | Main Actor | Stakeholders and Interest | Precondition | Minimal guaranties | Guaranties if success | Trigger | Main success scenario |  | Extensions |  | Data / Technology variations | Related Information
Unique ID of the use case. Base number is from Product Backlog | The name is the use case goal as a short active verb phrase | a longer statement of the context of use if needed, its normal occurrence conditions | Design scope, what system is being considered "black-box under design", can be a "Company" use case or a "Departament" use case or a "System" use case | Can be a summary use case or a user-goal or a sub function | A role name for the primary actor | List of stakeholders and key interest in the use case | what we expect is the state of the world | how the interest are protected under all exits(ie. Databse integrity maintained) | Success Criteria | what starts the use case | put here the steps of the scenario from trigger to goal delivery and any cleanup after | <step #><action description> | put here the extensions, one at a time, each referring to the step of the main scenario | <step altered><condition>: <action or sub use case> | put here the variations that will cause eventual bifurcation in the scenario | whatever necessary for additional information