EPRI Project 071103

CIM Testing Procedure Development

Minutes of the CIM Test Procedures Teleconference

Held on 01 February 2011 (2:00-3:00 EST)

# Meeting Summary

Weekly meeting of Project 071101 CIM Testing Procedure Development. Representatives from EPRI, AEP, BC Hydro, NIST, CISCO, and EnerNex attended.

# Agenda

- Progress since last meeting (meeting held on January 25, 2011)

- Issues arising during the previous week

- Verify progress against stakeholder expectations

- General issues discussion

- Expected work output during next week

- Action items for individuals

# Participants

The following people participated in the Teleconference:

| Name | Company |
| --- | --- |
| John Simmins | EPRI |
| David Willmon | NIST |
| Eric Mewhinney | BC Hydro |
| Frank Wilhuit | AEP |
| Bruce Muschlitz | EnerNex |
| Kay Stefferud | EnerNex |
| Al Hefner | NIST |
| Rich Stephenson | SCE |
| J. Combs | CISCO |
| Brad Singletary | EnerNex |
| Bill Moncrief | EnerNex |

# Progress since last meeting

- Reviewed and updated sample abstract test case

    - Walked through with group 1/18/2011

- Awaiting comments from Margaret Goodrich

- Updated and posted sample test procedure per comments received

- Documenting Virtual Lab procedures to connect systems at lab sites (e.g. MDMS at Site A & CIS at Site B)

- Consumers Site Support Guide initiated January 21.

- EPRI and other utilities (if desired) next

- Vender Site Support Guides started

- Entering Test Case documentation in Enterprise Architect

- Briefing can be found at: http://osgug.ucaiug.org/conformity/Shared%20Documents/CIM_TestingArtifacts/Presentations/20110201%20CIM%20Test%20Development%20Project%20Meeting.ppt

# Issues arising during the previous week

# Need reference set of interoperability requirements

# OpenSG Integration Requirements & Integration Sequence Diagrams

# SCE Use Cases

# Suggested Part-9 Reference Interface Requirements

# Need multiple venders to dry run procedures

# Verify progress against stakeholder expectations

- John briefed progress against stakeholder expectations:

- Task 3: Complete Mapping and Report for Extensions:

  - The deliverable includes a mapping spreadsheet and a report describing the use cases, extensions and implementation profiles.

  - For each OpenSG domain the tasks in support of the harmonization include:

  - Review and analyze all gaps between domain artifacts and the CIM.

  - Document proposed mapping and CIM extensions.

  - Implement the CIM extensions in UML.

  - Generate the profiles and other artifacts required for testing.

  - Create use cases (if they don’t already exist) to clarify the need for the extensions.

- Task 5: IOP these service definitions. List may not all be feasible:

  - CustomerMeterDataSet

  - EndDeviceAsset

  - EndDeviceControl

  - EndDeviceEvent

  - EndDeviceResponses

  - EndDeviceResponse

  - GetDeviceStatus

  - GetMeterReadings

  - MeterReadingSchedule

  - MeterReadings

  - MeterReading

  - MeterAssetConfig

# General Issues Discussion

- Brad Singletary walked through the Site Guide and explained the material to be documented for each test site.  Site guide will specify the information needed to setup virtual LANs between each test location.

- Kay walked through version 1 of the abstract test procedure.  The following comments were received and agreed upon.

  - 1)  Mark Ortiz requested that the test data set material be added.

  - 2) The recording of messages during formal test needs to be added to the test.

# Expected work output during next week

- Complete Site Support Guides

  - Consumers

  - EPRI

  - Initial vender

- Identify additional participants and schedule dry run of procedures

# Action items for individuals new and from previous weeks

| AI # | Assignee | Action | Status |
| --- | --- | --- | --- |
| 1 | John Simmins | Talk to Elster, Telvent, InterGraph, MillSoft. | In process |
| 2 | John Simmins | Work with internal resources to separate lab network completely from the EPRI operational network. | In process |
| 3 | Mark Ortiz | Have Shawn Hu send ADR/ADE info links. | Complete |
| 4 | Mark Ortiz | Set up EPRI server at EPRI. | In process |
| 5 | Kay Stefferud | Update Abstract Use Case with features from the Ft. Lauderdale abstract use case | Complete |
| 6 | Clint Powell | Find SCE representative for this group | Complete |
| 7 | Mark Ortiz | Provide written procedures on access to Consumer’s DMZ network and server | In process |
| 8 | Bruce Muschlitz | ADR/ADE link to group, part of these notes. | Complete |
| 9 | Bruce Muschlitz | Add Rrlowe@AEP.com, crodine@epri.com, jeff.gooding@sce.com to meeting minutes. | Complete |
| 10 | Kay Stefferud | Contract Mark Ortiz to request written procedures to access the Consumers server. | In process |
| 11 | Margaret Goodrich | Review sample abstract test case. | In process |
| 12 | Mark Ortiz | Send Kay excel spreadsheet with test set-up information. | In process |
| 13 | Bruce Muschlitz | Provide reference to X291 companion specs to be added to abstract test cases. | Complete |
| 14 | Kay Stefferud | Request CIM IOP IPR restrictions from IOP team. List, monitor and address set of network issues arising from connecting external vender servers to the Consumers and EPRI servers. Add SOW task references to schedule presented next week. | Complete |
| 15 | Mark Ortiz | Send Kay excel spreadsheet with test Point of Contact (POV) information. | In process |
| 16 | Kay Stefferud | Update concrete test procedures to include these four changes: 1. Add test data sets 2. Recording of data during test 3.Show both IEC functions and utility systems in sequence diagrams. 4. Change log title to Test Procedure | In process |
| 17 | Brad Singletary | Send Site Guide to Frank at AEP. | New |
| 18 | Kay Stefferud | Vet set of Part-9 interoperability requirements with Consumers and SCE. | New |