EPRI Project 071103

CIM Testing Procedure Development

Minutes of the CIM Test Procedures Teleconference

Held on 5 April 2011 (2:00-3:00 EST)

# Meeting Summary

Weekly meeting of the EPRI CIM Testing Procedure Development. Representatives from  EPRI, Consumers, AEP, SCE, IBM, CIM-PLE, Xtensible, Honeywell, Wowway, and EnerNex attended.

Good discussion today on the technical details including proper message patterns.

# Agenda

- Progress since last meeting

- Issues, opportunities and risks arising during the previous week

- Verify progress against stakeholder expectations

- General issues discussion

- Action items for individuals

- Expected work output during next week

# Participants

The following people participated in the Teleconference:

| Name | Company |
| --- | --- |
| Richard Stephenson | SCE |
| Frank Wilhoit | AEP |
| Kay Stefferud | EnerNex |
| John Simmins | EPRI |
| Bruce Muschlitz | EnerNex |
| Shaun Hu | Xtensible |
| John Adams | Honeywell |
| Mariza Maia | IBM |
| Gerald Gray | CIM-PLE |
| Paula Thompson | Wowway |
| Kostas Tolios | DTE Energy |
| Margaret Goodrich | Sisco |

# Progress since last meeting

- Mark Ortiz furnished VPN client for Consumers server

  - Windows 64 bit version available EPRI FTP site

  - Windows 32 bit version also needed

- Sample messages created

- Briefing can be found at: http://osgug.ucaiug.org/conformity/Shared%20Documents/CIM_TestingArtifacts/Presentations/2011-04-05%20CIM%20Test%20Development%20Project%20Meeting.ppt

# Issues arising during the previous week

Discussion centered on what was the best approach to develop the sample messages, how to select the correct message pattern and degree of testing fidelity. Overall it was decided that we would test against the test procedures.

# Verify progress against stakeholder expectations

# No change from last week.

# Expected Work Output During the Next Week

# Meeting with Consumers (Mark) and EnerNex (Kay)

# Consumer server login process

# Continue Sample Messages

# Sample message from IOP would be helpful

# Process to connect multiple test sites needs to be dry run

# Open Action Items for Individuals

| Assignee | Action | Status |
| --- | --- | --- |
| John Simmins | Work with internal resources to separate lab network completely from the EPRI operational network. | In process |
| Mark Ortiz | Provide written procedures on access to Consumer’s DMZ network and server | In process |
| Kay Stefferud | Contract Mark Ortiz to request written procedures to access the Consumers server. | In process |
| Margaret Goodrich | Review sample abstract test case. | In process |
| Mark Ortiz | Send Kay excel spreadsheet with test set-up information. | In process |

# Action items for individuals new and from previous weeks

| AI # | Assignee | Action | Status |
| --- | --- | --- | --- |
| 1 | John Simmins | Talk to Elster, Telvent, InterGraph, MillSoft. | Complete |
| 2 | Mark Ortiz | Have Shawn Hu send ADR/ADE info links. | Complete |
| 3 | Kay Stefferud | Update Abstract Use Case with features from the Ft. Lauderdale abstract use case | Complete |
| 4 | Clint Powell | Find SCE representative for this group | Complete |
| 5 | Bruce Muschlitz | Add Rrlowe@AEP.com, crodine@epri.com, jeff.gooding@sce.com to meeting minutes. | Complete |
| 6 | Bruce Muschlitz | Provide reference to X291 companion specs to be added to abstract test cases. | Complete |
| 7 | Kay Stefferud | Request CIM IOP IPR restrictions from IOP team. List, monitor and address set of network issues arising from connecting external vender servers to the Consumers and EPRI servers. Add SOW task references to schedule presented next week. | Complete |
| 8 | Mark Ortiz | Send Kay excel spreadsheet with test Point of Contact (POV) information. | Complete |
| 9 | Kay Stefferud | Update concrete test procedures to include these four changes: 1. Add test data sets 2. Recording of data during test 3.Show both IEC functions and utility systems in sequence diagrams. 4. Change log title to Test Procedure | Complete |
| 10 | Brad Singletary | Send Site Guide to Frank at AEP. | Complete |
| 11 | Kay Stefferud/ John Simmins | Schedule PMO meeting with John Simmins, Robert Sarfi, Kay Stefferud and Bruce Muschlitz | Complete |
| 12 | Bruce Muschlitz | ADR/ADE link to group, part of these notes. | Complete |
| 13 | John Simmins | Work with internal resources to separate lab network completely from the EPRI operational network. | In process |
| 14 | Mark Ortiz | Set up EPRI server at EPRI. | Complete |
| 15 | Mark Ortiz | Provide written procedures on access to Consumer’s DMZ network and server | In process |
| 16 | Kay Stefferud | Contract Mark Ortiz to request written procedures to access the Consumers server. | In process |
| 17 | Margaret Goodrich | Review sample abstract test case. | In process |
| 18 | Mark Ortiz | Send Kay excel spreadsheet with test set-up information. | In process |
| 19 | Kay Stefferud | Vet set of Part-9 interoperability requirements with Consumers and SCE. | In process |
| 20 | Kay Stefferud | Provide recommendation on which version of the Part 9 to use as a baseline for the EPRI CIM testing. | Complete |
| 21 | Kay Stefferud, Bruce Muschlitz | Review the services used in the test procedures and verify that the services referenced are correct | Complete |