- Attendance

If you are on the phone but not logged on to the webinar, please send an email to charlesr.smith@ge.com so your attendance can be recorded.

| Company | Name | 12-Jan | 19-Jan | 26-Jan | 16-Feb | 2-Mar |
| --- | --- | --- | --- | --- | --- | --- |
| 4home | Steve Hindman |  |  |  |  |  |
| Aclara | Luis Pizano | 1 |  | 1 |  |  |
| AEP | Barry Pierce |  |  |  |  |  |
| AEP | Jorge Melean |  |  |  |  |  |
| APS | Nilesh Kulkarni |  |  |  | 1 |  |
| Aridhio Technologies | Antonio Ranson |  |  |  |  |  |
| BGE | Kyle Carson |  |  |  |  |  |
| BGE | Jim Garrett |  |  |  |  |  |
| BSH | Larry Bell |  |  |  |  |  |
| BSH | Kirat Bakshi |  |  |  |  |  |
| Capgemini | David Mulder |  |  |  | 1 |  |
| Carrier | Ray Archacki |  |  |  |  |  |
| CenterPoint / IBM | Andy Laskowski |  | 1 | 1 | 1 |  |
| CenterPoint | Jim Sheppard |  |  | 1 |  |  |
| Cisco | Chuck Duffy |  |  |  |  |  |
| Cisco | Tom Herbst |  |  |  |  |  |
| Coincident, Inc | Jason Hanna |  |  |  | 1 |  |
| Comverge, Inc. | Brian Wright |  |  |  | 1 |  |
| Comverge, Inc. | Howard NG |  |  |  | 1 |  |
| Consumers Energy | Brad Singletary |  |  |  |  |  |
| Certicom Corp | Matthew Campagna |  |  |  |  |  |
| DotUI | Ishak Kang | 1 |  |  |  |  |
| DotUI | Ken Fromm |  |  |  |  |  |
| DotUI | Christopher Sater |  |  |  |  |  |
| Duke | Gary Stuebing | 1 |  |  |  |  |
| Deloitte Consulting | Michael Northern |  |  |  |  |  |
| Drummond Group | Timothy Bennett |  |  |  | 1 |  |
| Eaton | Brandon Rogers |  |  |  |  |  |
| EcoLogic | Chris Kardos |  |  |  |  |  |
| Emerson White Rogers | David Drew |  |  |  |  |  |
| emeter | Chris King |  |  |  |  |  |
| EnerNex | Erich Gunther |  |  |  |  |  |
| EnerNex | Bradley Singletary |  |  |  | 1 |  |
| EPRI | Brian Seal |  |  | 1 | 1 |  |
| FPL | George Cosio |  |  |  |  |  |
| FPL | William King |  |  | 1 |  |  |
| GE | Charles Smith | 1 |  |  |  |  |
| GE | Nate Littrell |  | 1 |  |  |  |
| GE | Robby Simpson | 1 |  |  |  |  |
| Georgia Power Company | Larry Barto |  |  |  |  |  |
| google | Charles Spirakis |  |  |  |  |  |
| Gridata Inc | Michael Leppitsch |  |  |  |  |  |
| heyCoop, LLC | Mike Coop |  |  | 1 | 1 |  |
| Home Automation, Inc | Ron Gumina | 1 | 1 | 1 |  |  |
| Honeywell | Clay Amb |  |  |  |  |  |
| IBM | Javier Torres |  | 1 |  |  |  |
| IBM | Tim Deloach |  | 1 |  |  |  |
| I’m in Control | Kirk Oatman | 1 | 1 | 1 | 1 |  |
| Invaluable Technologies | Harpreet Kachroo |  |  |  |  |  |
| Itron | Steve Johnson |  |  |  |  |  |
| Kaapco / ASR Systems | Anuj Puri |  |  | 1 |  |  |
| KCP&L | Ed Hedges |  |  |  | 1 |  |
| Konnected Universe LLC | Afshin Amini |  |  |  |  |  |
| LG Electronics U.S.A. Inc. | Christopher Johnson |  |  |  |  |  |
| LG Electronics U.S.A. Inc. | Koonseok Lee |  |  |  | 1 |  |
| LonMark International | Jeremy J. Roberts |  |  |  | 1 |  |
| MicroSoft | MJ Miller |  |  |  |  |  |
| MicroSoft | Chad Maglaque |  |  |  | 1 |  |
| MultiSpeak | Gary McNaughton |  |  |  |  |  |
| Oncor | Brad Johnson |  |  |  |  |  |
| Oncor | Larry Kohrmann |  |  |  |  |  |
| Panasonic | Chenyi Chiu |  |  |  |  |  |
| Panasonic | Todd Rytting |  |  | 1 |  |  |
| Pentair Water Pool & Spa | Brian Boothe |  |  |  |  |  |
| People Power | Yvan Castilloux |  |  |  | 1 |  |
| PG&E | Phil Beecher | 1 |  |  |  |  |
| PG&E | Zahra Makoui |  | 1 |  |  |  |
| Portland General Electric | Conrad Eustis |  | 1 |  | 1 |  |
| Progress Energy | Bill Godwin |  |  |  |  |  |
| Proto6 | Geoff Mulligan |  | 1 | 1 |  |  |
| Reliant | Mary Zientara | 1 | 1 | 1 | 1 |  |
| Reliant | Brent Hodges |  |  |  |  |  |
| Reliant | Mark Smith |  |  |  | 1 |  |
| RIM | David Jackson |  |  |  |  |  |
| SCE | Steve Van Ausdall |  | 1 |  | 1 |  |
| SCE | Ivan O'Neill |  |  |  |  |  |
| Schneider Electric | Mike Matthews |  |  |  | 1 |  |
| Schneider Electric | Gary Kuzkin |  |  |  | 1 |  |
| SDG&E | JC Martin |  |  | 1 |  |  |
| Sensus | David Willcox |  |  |  |  |  |
| Sensus | Richard Pate |  |  |  |  |  |
| Sensus | Tom Pautz |  |  |  |  |  |
| SG Insights | Joe Ballif |  |  |  | 1 |  |
| SouthWest Research | John Wood | 1 |  |  |  |  |
| Subzero | Steven Nackers |  |  |  |  |  |
| Tendril | Mike Peacock |  |  |  |  |  |
| Tendril | David Mollerstuen |  |  |  |  |  |
| Trilliant | Nathan Ota | 1 | 1 | 1 | 1 |  |
| UISOL | Jens Winkel |  |  |  | 1 |  |
| U-SNAP Alliance | Barry Haaser |  |  |  | 1 |  |
| Visible Energy | Marco Graziano |  |  |  |  |  |
| Xtensible.net | Wayne Dennison |  |  |  |  |  |
| Zigbee | Tobin Richardson |  |  |  |  |  |
|  | Bruce Muschlitz |  |  |  |  |  |
|  | Carl Besaw |  |  |  |  |  |
|  | Mike Howard |  |  |  |  |  |
| Total |  | 11 | 11 | 13 | 27 |  |

- Status of Action Items

| # | Date | Action Item | Assigned to | Status |
| --- | --- | --- | --- | --- |
| AI-32 | 2-3-10 | Send Kay Stefferud OpenHAN use cases | Steve Van Ausdall |  |
| AI-32 | 2-4-10 | Draft a PEV section for the OpenHAN SRS 2.0 by Feb 12th | Tom Hebst (Cisco) Nate Ota (Trilliant) Aaron Martlage (plug smart) Davie DeYagher (BC Hydro) | 1st draft complete; |
| AI-33 | 2-4-10 | Review OpenHAN SRS Sections 1, 2, and 3 and submit updates to document editing team | Rajiv Singhal (Cisco) Mary Zientara (Reliant Energy) | Section 2,3 revisions complete; Section 1 revisions still being drafted; |
| AI-34 |  |  |  |  |

3.	Next steps - timeline

| Date | Activity |
| --- | --- |
| March 2 | Document editing team to finish reviewing comments from Itron and BC Hydro (1 to 3 p.m. Central) |
| March 3 | Document editing team to review comments from People Power and CenterPoint Energy (1 to 3 p.m. Central) |
| March 10-11 | Document editing team to meet F2F to work on Appendix 4.2 Device Mapping and Sections 1, 2, 3 and incorporate into the 1.91 document |
| March 19 | v1.91 available for comment |
| March 30 | Comments on v1.91 due |
| April 9 | Document editing team to review comments and make v1.92 available for comment |
| April 16 | Comments on v1.92 due |
| April 23 | Document editing team to review comments and make v1.93 available for review at OpenSG F2F |
| April 26-29 | OpenSG F2F meeting Review OpenHAN v1.93 in OpenHAN work sessions OpenHAN TF vote on OpenHAN v1.93 |
| April 29 | OpenHAN TF vote on OpenHAN SRS v2.0 |
| May 7 | Sent to OpenSG for ratification of OpenHAN 2.0 |
| May 14 | Submit to NAESB Smart Grid Task Force |

4.	Update from Use Case Team

5. 	Update from Document Editing Team

- PEV section

- Sections 1, 2, 3

-	Appendix 4.2 Logical Device Mapping table (pg 90)

  - Devices – ESI, PCT, Display, EMS, Load Control, HAN Electric Meter, HAN Meter (non-electric), Smart Appliance

  - Others?? – Electric Vehicle Supply Equipment (EVSE)

- Comments received are posted at OpenHAN 2.0 doc comments.  Document editing team comments are placed into the comment form and saved in the comment f older.

6.   Next meeting

- Next OpenHAN 2.0 meeting will be March 16, 2010 at 11 a.m. Central. Conflicts with SGIP F2F.

- Document editing team meetings will be announced on the OpenHAN sharepoint and through the listserv.

- March 10-11 F2F meeting.  Only 1 has signed up to attend.  Discuss canceling the F2F and setting up several 2 hour webinars instead.

7. 	Adjourn at noon Central